Action Plan for Implementing the Convention on Biological Diversity’s

Programme of Work on Protected Areas

( Ethiopia)

Submitted to the Secretariat of the Convention on Biological Diversity [29/03/2012]

Protected area information:

Lead implementing agency: (Institute of biodiversity Conservation; Ethiopian wildlife Authority; Regional forest and wildlife Agency; Regional Culture and tourism; Regional Environmental Protection Authority; Regional Bureau of Agriculture)

Multi-stakeholder committee: (No)

Description of protected area system

# National Targets and Vision for Protected Areas

The country’s vision for protected areas include a perpetual existence of biological diversity in effectively managed protected area systems for enhanced ecological, cultural benefits of local, national, and global communities. In Ethiopia, protected areas are an integral part of sustainable development providing protection to centerpieces of wider landscapes and watersheds as source of important ecosystem services and climate change adaptation and mitigation. Further, they act as refuges for species and ecological processes that can not survive in intensely managed landscapes. Often, they provide other essential benefits for local communities and as well as the national economy at large.

National Aichi Related Targets

- By 2015, two corridors will be created, especially in the transboundary terrestrial protected areas as a contribution to enable climate change resilience of PAs

- Encourage the establishment of ten more protected areas that benefit indigenous and local communities by 2016.

- By 2018, undergo economic valuation for some five established protected areas.

- By 2015, mainstream protected areas into national development plans and programs

- By 2014, have management plans for 30 % protected forests

Coverage

Ethiopia has several designated Protected Areas (PAs) including 15 national parks (20,833 km²); three wildlife sanctuaries (9,532 km²), 11 wildlife reserves (24,810 km²) and 18 controlled hunting areas (131,820 km²). The government has committed to designate over 193,000 km2 (16.5% of the total area of the country) in order to increase the protection of the wildlife resources of the country. Ethiopia has 58 National Forest Priority Areas (48,000 km²).  Many more forests are now designated as protected areas. Although the primary objective of NFPA is to conserve the country's remaining forests, they are extremely valuable in sheltering large numbers of species, including some that are not found in the wildlife conservation areas.

Description and background

(Ethiopia is one of the countries with richest biodiversity in the world.  It has diverse physical features that cause a wide variation in climatic conditions. The flora of the country is very heterogeneous and has rich endemic elements. There are more than 6000 higher plant species, of which about 10-12 percent is endemic. The faunal diversity of the country is also rich. Important flagship species, endemic to Ethiopia include the Ethiopian wolf (Canis simensis), walia ibex (Capra walie), Gelada baboon (Theropthecus gelada), Giant lobelia (Lobelia rhyncopetalum) amongst others.

However, habitat loss, including degradation and fragmentation, continues to be the main driver of biodiversity loss. Thus, collaborative effort is required to conserve and maintain the sustainability and integrity of the biodiversity and their ecosystem. The Convention on Biological Diversity (CBD) recognizes in situ or PA as primary approach to biodiversity conservation. Of particular importance is the balance to be struck between conservation measures within Protected Areas (PAs) and measures for sustainable use of natural areas outside (PAs). Protected areas, together with conservation, sustainable use and restoration initiatives in the wider land-and seascape are essential components in national and global biodiversity conservation strategies. They provide a range of goods and ecological services while preserving natural and cultural heritage. They can contribute to poverty alleviation by providing employment opportunities and livelihoods to people living in and around them. These inherent assets attract nature-lovers around the world, thereby promoting the flourishing of a new form of tourism in the country ecotourism.

The establishment and management of a representative and effectively managed system of protected areas is a key strategic approach in the conservation of Ethiopia’s biodiversity and in the mitigation of the impacts of climate change on biodiversity. The country has established a number of protected areas since 1960’s. According to published report, about 14% of the total land area of the country is designated as protected area. These include parks, sanctuaries, protected forest, and controlled hunting areas. However, these resources need extensive and representative systems of Protected Areas that maintain biological values as well as ensuring a continued flow of ecosystem goods and services. Despite being officially protected, these areas are generally marked by weak management capacity and continually degraded landscapes. The majority of these PAs has shrunk due to population pressure: crop cultivation, grazing, settlement, and deforestation. The existing management of the PAs is under federal and regional government mandates. Most protected areas need considerable capacity and support to implement and overcome the huge challenges and threats encountered.

Governance types

In Ethiopia protected areas are managed by different bodies. Some PAs are protected by federal government agency such as Ethiopian Wildlife Conservation (EWCA). Some of the PAs are managed by regional offices of forest and wildlife conservation agencies or bureaus. Some PAs are managed by indigenous and rural communities residing near by PA.  However, most of the PAs are currently managed under government-community joint management system.

Key threats

The major threats to the protected areas and its associated biodiversity are unsustainable utilization of natural resources (over-harvesting), deforestation, conversion of natural vegetation to farmland, expansion of commercial farm, forest  fires, settlement /encroachment,  invasive species, illegal trafficking of domestic and wild animals, poaching, wetland destruction and climate change. These threats can be broadly linked to the following categories: limited governmental, institutional, and legal capacity; population growth; land degradation; weak management of protected areas. They are largely interrelated and self-reinforcing, and it is therefore important not only to understand the individual threats but also to examine them in a holistic fashion that recognizes their interrelation and can help to propose solutions to decrease the threats and mitigate their effects. But most of these are related to the root causes of poverty, which are lack of alternative viable livelihoods, increasing population pressure and inadequate awareness of the threats and possible solutions at all levels.

Barriers for effective implementation

- Weak institutional Interaction

- Most of the protected areas are under weak management, inadequate institutional collaboration as well as inadequate funding. There is lack of cooperation between the institutions/organizations involved in protected area management. There is also lack of institutional coordination in PA management with multiple institutions administering and influencing protected areas and conservation. There has been inadequate communication with key stakeholders at the federal and national regional state levels, as well as with NGO’s, communities and the private sector. The PA system is complex with responsibilities across different federal and regional institutions resulting in overlap and conflicting mandates. These impede effective management of PA system in the country.  Many of these relate to inadequate human capacity and financial resources.

- PA is not well integrated in sectoral planning

Line ministries and institutions have the responsibility with respect to their own sectors and cross-sectoral natural resource and environmental management, including accounting for PAs in sectoral plan development. However, this is not well addressed in sectoral planning.

c.              Lack of PA management plans

Management plans have been prepared for very few protected areas in Ethiopia. The majority of the PAs don’t have management plan, which affect effective management.

d.   In adequate law-enforcement

Legislation designed to protect the PAs has proven very difficult to enforce under the existing conditions.

Status, priority and timeline for key actions of the Programme of Work on Protected Areas

# Status of key actions of the Programme of Work on Protected Areas

| Status of key actions of the Programme of Work on Protected Areas | Status |
| --- | --- |
| Progress on assessing gaps in the protected area network (1.1) | 3 (final draft of the study is ready for some parks |
| Progress in assessing protected area integration (1.2) | 0 |
| Progress in establishing transboundary protected areas and regional networks (1.3) | 2 (there is discussion on two trans boundary PAs; Alatish & Gambella parks) |
| Progress in developing site-level management plans (1.4) | 1 (most of the PAs have no management plans except Bale and Simien parks. Most forest PAs have participatory management plan but lack scientific approach |
| Progress in assessing threats and opportunities for restoration (1.5) | 1, there is on going effort |
| Progress in assessing equitable sharing of benefits (2.1) Progress in assessing protected area governance (2.1) | 2 (is established in some PAS) 2 ( is done in some PAs particularly in forest governance) |
| Progress in assessing the participation of indigenous and local communities in key protected area decisions (2.2) | 3 (is being implemented) |
| Progress in assessing the policy environment for establishing and managing protected areas (3.1) Progress in assessing the values of protected areas (3.1) | 3 ( Is underway for both wildlife and forest PAs) |
| Progress in assessing protected area capacity needs (3.2) | 3 (Done for some wildlife PAs not for forest PAs) |
| Progress in assessing the appropriate technology needs (3.3) |  |
| Progress in assessing protected area sustainable finance needs (3.4) | 3 (done for some wild life PAs but not for forest PAs) |
| Progress in conducting public awareness campaigns (3.5) | 2 There has been campaigns during tourism day celebration |
| Progress in developing best practices and minimum standards (4.1) | 0 |
| Progress in assessing management effectiveness (4.2) | 2 (for few wildlife and forest PAs) |
| Progress in establishing an effective PA monitoring system (4.3) | 0 |
| Progress in developing a research program for protected areas (4.4) | 0 |
| Progress in assessing opportunities for marine protection | 0 (no marine PA) in the country |
| Progress in incorporating climate change aspects into protected areas | 3 study has been conducted for all PAs |

Status: 0 = no work, 1 = just started, 2 = partially complete, 3 = nearly complete, 4 = complete

(Insert notes as appropriate)

# Priority actions for fully implementing the Programme of Work on Protected Areas:

Action 1 Assess threats and opportunities for restoration

Action 2 Developing site-level management plans

Action 3 Capacity needs assessment of protected area

Action 4 Research in protected areas

Action 5 Valuation of protected area

Action 6 Encourage the establishment of ten more protected areas that benefit indigenous and local

Timeline for completion of key actions

Action 1 Assessing threats and opportunities for restoration (2013-2016)

Action 2 Developing site-level management plans (2013-2016)

Action 3 Capacity needs assessment of protected area (2013-2015)

Action 4 Research in protected areas (2013-2018)

Action 5 Valuation of protected areas (2013-2016)

Action 6 Encourage the establishment of ten more protected areas that benefit indigenous and local (2013-2016)

# Action Plans for completing priority actions of the Programme of Work on Protected Areas

(Insert detailed action plans)

Action 1: (Assessing threats and opportunities for restoration)

| Key steps | Timeline | Responsible parties | Indicative budget in (USD) |
| --- | --- | --- | --- |
| Assess the status of key biodiversity including the population, distribution and ecological systems | 2013 | EWCA, IBC, Regional PA sectors , Universities NGOs | 120,000 |
| Map the distribution and intensity of threats and their impacts on focal biodiversity features | 2014 | EWCA, IBC, Regional PA sectors , NGOs, Universities | 20,000 |
| Analyze the results of the threat assessment | 2015 | EWCA, IBC, Regional PA sectors , NGOs | 5,000 |
| Analyze the opportunities for restoration | 2015 | EWCA, IBC, Regional PA sectors , NGOs | 5,000 |
| Prioritize threats based on their overall contribution to the loss of biodiversity as well as their feasibility | 2015 | EWCA, IBC, Regional PA sectors , NGOs | 5,000 |
| Develop an action plan for threat prevention and implementation | 2016 | EWCA, IBC, Regional PA sectors , NGOs | 20,000 |
| Monitor changes in the status of protected area threats | 2016-2020 | EWCA, IBC, Regional PA sectors , | 15,000 |

Action 2: (Developing site-level management plans)

| Key steps | Timeline | Responsible parties | Indicative budget in (USD) |
| --- | --- | --- | --- |
| Define the objective and expected out put, assess and collect data on ecological, social, biological situation | 2013 | EWCA, regional PA offices, NGOs | 70,000 |
| Evaluate (analyze) data | 2014 | EWCA, regional PA offices | 5,000 |
| Identify constraints, opportunities, and threats | 2015 |  | 5000 |
| Develop draft plan with participation of local communities | 2015 |  |  |
| Conduct national and local stakeholder consultations, through a series of workshops, to ensure the incorporation of ideas and concerns from local communities | 2015 | EWCA, regional PA offices, other stakeholders | 20,000 |
| Publish the final management plan | 2016 | EWCA, regional PA offices, other stakeholders | 8,000 |
| Revision of draft and develop final management plan and get approval of the plan | 2016 | EWCA, regional PA offices, other stakeholders (NGOs) | 10,000 |

Action 3: (Capacity needs assessment of protected area)

| Key steps | Timeline | Responsible parties | Indicative budget (USD) |
| --- | --- | --- | --- |
| Identifying capacity gaps hindering effective PA management | 2012 | EWCA, regional PA offices, IBC | 10,000 |
| Analyze and prioritize the capacity gaps and select the most important gap to work on | 20 13 | EWCA, regional PA offices, IBC | 2,000 |
| Conduct training to the different staff members of PAs | 2014-2015 | EWCA, regional PA offices, IBc | 25,000 |
| Evaluate changes in PA management | 2016-2020 | EWCA, regional PA offices | 2,000 |

Action 4: (Research in protected areas)

| Key steps | Timeline | Responsible parties | Indicative budget (USD) |
| --- | --- | --- | --- |
| Reviewed pertinent literature regarding biological, socio-economic and biophysical situations of PA | 2013 | EWCA, IBC, universities | 4,000 |
| Identify research gaps and priorities | 2013 | EWCA, IBC, universities | 4,000 |
| Conduct research on priority issues | 2014-2018 | EWCA, IBC, universities | 30,000 |
| Compile and disseminate research findings | 2014-2018 | EWCA, IBC, universities | 15,000 |

Action 5 (Valuation of protected areas)

| Key steps | Timeline | Responsible parties | Indicative budget (USD) |
| --- | --- | --- | --- |
| Reviewed pertinent literature regarding biological, socio-economic and biophysical situations of PA | 2013 | EWCA, IBC, universities | 40,000 |
| Conduct valuation studies in PAs | 2013-2016 | EWCA, IBC, universities | 120,000 |
| Analyze valuation data | 2017 | EWCA, IBC, universities | 5,000 |
| Communicate findings of the study to stakeholders particularly to decision makers | 2018 | EWCA, IBC, universities | 10,000 |

Action 6 (Encourage the establishment of ten more protected areas that benefit indigenous and local)

| Key steps | Timeline | Responsible parties | Indicative budget (USD) |
| --- | --- | --- | --- |
| Consultation workshop with relevant stakeholders | 2013 | EWCA, regional PA offices, IBC | 10,000 |
| Assess the status of key biodiversity and ecological systems | 2014 | EWCA, regional PA offices, IBC | 10,000 |
| Analyze, compile and communicate the results of assessments | 2015 | EWCA, regional PA offices, IBC | 5,000 |
| Conduct a topographic survey of the proposed boundaries and map them | 2015 | EWCA, IBC, u | 20,000 |
| Consultation workshop with relevant stakeholders and local communities | 2016 | EWCA, regional PA offices, IBC | 30,000 |
| Demarcation of the boundaries of the proposed protected areas | 2016 | EWCA, regional PA offices, IBC | 5,000 |

Key assessment results

Ecological gap assessment

Originally, the protected area system of the country had not been designed with scientific concepts of biodiversity and its optimal representation protected areas in mind. Like in most countries, it had developed over the years on the basis of educated guesses by wildlife managers, as to where diversity (mainly large mammal diversity) was located and where tracts of land were still available for protection that would not conflict too much with other land uses.

Management effectiveness assessment

Management effectiveness has been conducted for 10 protected areas in 2010/2011 and the result is compiled. For some, the result is compared with their corresponding result in 2008 but not for those that do not have a base line. According to the assessment result, all do not have management plan and business plans but two; Bale and Simien. In all protected areas the major problem is community pressure from over grazing, poaching, fire wood collection, illegal settlement and farming.  On average their score is 35% which is very low.

Sustainable finance assessment

In order to ensure sustainable financing of protected areas, study on different sustainable financial options was conducted. Accordingly, Business plan for Ethiopian protected Area system was developed.

Policy environment assessment

Although arrays of policy, strategy and proclamations exist, there are still areas that need explicit legal provisions regarding the modalities of public-private partnerships. Particularly, co-management governance systems, national categorization of protected areas, finance mechanisms, resettlement issues for community members who settled within protected areas in the recent past. At federal and regional level various policies and proclamations were passed based on assessment of gaps. However, the existing enabling environment still showed gaps.

Protected area integration and mainstreaming assessment

The national protected area system is not explicitly accommodated in the programme. The Plan for Accelerated and Sustainable Development to End Poverty (PASDEP, recognizes the linkage between environmental degradation and poverty levels and does focus on the conservation of natural resources, including water, soil and energy. The recently developed Growth and Transformation Plan (GTP) of the country give due attention for conservation of natural resources.

Protected area valuation assessment

Protected area valuation assessment have been conducted and the assessment revealed that

- The value of protected areas is far greater in terms of environmental services (e.g. climate stabilization, electricity production, water services, etc.) than the value of direct benefits through tourism and employment.

- The value of benefits provided by protected areas to the national economy by far exceed the current budget provided by central government of US$ 1.3 million (ETB 16.1 million, budget 2009/10) and warrants increased investment to raise management effectiveness in order to ensure the continuous flow of services, provided by protected areas.

- Benefits derived from protected areas in the form of environmental services, and their importance for sustainable economic development and poverty reduction, have been undervalued and have not received due attention.

Climate change resilience and adaptation assessment

Climate change has become a global challenge for nature conservation due to its impacts on species, habitats and ecosystems.  A vulnerability assessment of on some protected areas in Ethiopia was conducted by a team of experts from Ethiopian wild life conservation Authority (EWCA).  Based on the assessment four protected areas, namely, Bale Mountain National Park, Simien Mountain National Park, Abijatta-Shalla Lakes National Park and Awash National Park was selected for climate change adaptation. Accordingly, four strategic adaptation themes were developed.